## GCP Plan
Terraform Module - Memorystore for Valkey Project Plan (Executive View) Goal: Build, test, validate and deliver a production-ready, self-service Terraform module that any consumer team can use to provision a fully-configured Valkey cache cluster on GCP.
PHASE | SPRINT | TASK | SubComments | Start (date) | Finish (date) | Completed / Pending | Owner | Key Contacts ( Dependency)
PHASE 0 – Requirements & Discovery | Sprint 1 (6/24-7/7) | GCP Memorystore Architecture Documentation | Documented network topology, PSC connectivity model, subnet allocation strategy, and overall Memorystore Valkey architecture. | 6/24/2026 | 7/7/2026 | Completed | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| Sprint 2 (7/8-7/21) | Access, IAM & Platform Discovery | Achieved: GitHub repo access (Terraform template repo), GCP RBAC role assignment, AD group membership to GCP admin groups, personal system account access, and GCP service account RBAC role assignments. VPC/subnet/firewall/API enablement and Terraform deployment readiness also completed; alerting/notification config remains pending (see Observability). | 7/8/2026 | 7/21/2026 | Completed | Satishkumar Sivakumar | Vicky Baldock (Approvals), Siva Rajadurai
| Sprint 2 (7/8-7/21) | Consumer Requirements & Production Standards | Intake form variables defined. Production standards set: TLS via Google-managed CA certificates, IAM auth via the current manual GCP-group + databaseconnectionuser role process, and PSC-based private-only networking confirmed via existing connection policies. | 6/29/2026 | 8/13/2026 | Completed | Satishkumar Sivakumar | Siva Rajadurai
PHASE 1 – Module Design | Sprint 1 (6/24-7/7) | Module Design, Outputs & Dependency Planning | Defined module structure, root/sub-module mapping, naming conventions, and input/output interfaces (PSC endpoint details, connection endpoints, notification channels). Networking and IAM identified as the primary execution dependencies: Networking Readiness → Core Deployment → IAM Bindings. | 6/24/2026 | 7/7/2026 | Completed | Satishkumar Sivakumar
PHASE 2 – Module Build | Sprint 3 (7/22-8/4) | Terraform Module Build (Core Resources, Inputs, Guardrails) | Built and validated ~40+ input variables, core Memorystore Valkey resource deployment, backup/data-protection configuration, maintenance windows, and production guardrails (deletion protection, private-only access, secure defaults). | 7/22/2026 | 8/4/2026 | Completed | Satishkumar Sivakumar
| Sprint 3 (7/22-8/4) | Module Extraction & Terraform Registry Publish | Extracted the reusable module from the root directory and published it to the Terraform registry. Successfully deployed and validated all three modes — Standalone, HA, and DR. | 7/22/2026 | 8/4/2026 | Completed | Satishkumar Sivakumar
| Sprint 3 (7/22-8/4) | Consumer Onboarding (Self-Service JSON Intake) | Implemented JSON-based onboarding pattern (request_type: create/delete). Three consumer templates now exist — Humit, CenterWell, SHRDServices. Humit fully tested end-to-end: intake validated, instance creation confirmed, PSC endpoint attached, connection endpoints generated. | 7/30/2026 | 8/13/2026 | Completed | Siva Rajadurai/ Satishkumar Sivakumar
| Sprint 3 (carried to 6) | Observability & Alerting | Alert module in progress: memory/CPU thresholds, node health, replication lag, connection spikes/errors, integrated with Cloud Monitoring. ROADBLOCK: Terraform service account lacks required IAM roles (roles/monitoring.alertPolicyEditor, roles/monitoring.notificationChannelEditor) to create/manage alert policies — awaiting role grant. | 7/22/2026 | 9/15/2026 (probable) | Blocked | Satishkumar Sivakumar
| Sprint 4 (8/5-8/18) | Module Refactor – Reusable Submodules & API-Compatible Templates | Module refactored and ready for testing. Happy-path deployment validated; Siva's wrapper API pre-defines required variables, reducing configuration risk. KNOWN ISSUE: DR-scenario validation surfaced Memorystore provisioning Error Code 8. Workaround identified: clean up instance metadata in the GCP console and rerun Terraform. | 8/5/2026 | 8/18/2026 | Completed | Satishkumar Sivakumar | Siva Rajadurai (Wrapper API)
| Sprint 5 (8/19-9/1) | IAM Access Model – Consumer Instance Scoping | Consumer IAM groups will request the dbconnectionuser role via RFA — the same flow customers will use in production. Open item: design an access model so each group can connect only to its own instance(s), not other consumers' instances. | 8/19/2026 | 9/1/2026 (probable) | In Progress | Satishkumar Sivakumar
| Sprint 6 (9/2-9/15, probable) | KMS / Data Encryption (CMEK) | Enable customer-managed encryption for data at rest. Need the Memorystore Google-managed service agent granted the appropriate KMS role (likely roles/cloudkms.cryptoKeyEncrypterDecrypter) and the Terraform service account granted KMS key-creation access. Exact role requirements still being confirmed. |  | 9/15/2026 (probable) | Pending | Satishkumar Sivakumar
PHASE 3 – Testing & Validation | Sprint 3 (7/22-8/4) | Code Testing & Validation (Static, Deployment, Idempotency, Update) | Terraform validation/linting, Dev deployment testing, repeat-apply idempotency checks, and in-place update testing all passed with no destructive changes. | 7/22/2026 | 8/4/2026 | Completed
| Sprint 5 (8/19-9/1) | Connectivity & Network Validation | Testing connectivity from local machine, on-prem VMs, Azure, and GCP. Firewall ticket raised to open port 6379. BLOCKER: Firewall team confirmed the Memorystore endpoint address is not on the routing table. Pending Network Team (Justin Hulsman) to add the routing entry and DNS Team (Narendra) to complete DNS/route configuration before Firewall can open port 6379. | 8/19/2026 | 9/1/2026 (probable) | Blocked | Satishkumar Sivakumar | Justin Hulsman (Network Team), Narendra (DNS Team)
PHASE 4 – Production Readiness | Sprint 3 (7/22-8/4) | Code Quality | Zero validation errors, no hardcoded values, all variables documented, no secrets in code. Code quality validation passed for the Valkey module. | 7/22/2026 | 8/4/2026 | Completed | Satishkumar Sivakumar
| Sprint 6 (9/2-9/15, probable) | Functional & Security Validation | Functional: instance creation, PSC reachability, alerting, backup restore. Security: no public endpoints, TLS enforced, IAM auth configured, deletion protection enabled. Depends on resolution of the connectivity blocker and the Observability roadblock. |  | 9/15/2026 (probable) | Not Started
| Sprint 7 (9/16-9/29, probable) | Stakeholder Sign-Off | Final approvals required from Cloud, Network, Security, and IMDG teams before production rollout. |  | 9/29/2026 (probable) | Not Started |  | Cloud Team, Network Team, Security Team, IMDG Team
SUCCESS CRITERIA |  | All 4 phases are successfully delivered
All stakeholder sign-offs are obtained
Terraform module is production-ready and reusable
Consumer intake process is implemented
Module is handed over to Siva's Team
|  | Post-Deployment Success Criteria | Monitoring alerts functioning correctly No unexpected cost spikes Backups exist and are restorable Stable performance in production