## Overview
Valkey Terraform Module — Program Status Overview Self-service, production-ready Terraform module for Google Cloud Memorystore for Valkey, rolling out across Dev → QA → UAT → Prod
Snapshot date: | 7/28/2026
Environment | Completed | In Progress | Pending / Blocked | Not Started
Dev | 8 | 2 | 10 | 9
QA | 0 | 0 | 0 | 29
UAT | 0 | 0 | 0 | 29
Prod | 0 | 0 | 0 | 29
Program Structure
Phase 0 — Requirements Gathering | Access, architecture, IAM/networking design, team & standards alignment.
Phase 1 — Module Design (Architecture) | Module structure/mapping, dependency sequencing, and required outputs. ("Module Structure" was folded into "Module Mapping" — duplicate, no independent tracking value.)
Phase 2 — Code Build Stage (Implementation) | Terraform build-out: variables, core resource, data protection, IAM, guardrails, observability, and the self-service consumer onboarding pattern.
Phase 3 — Code Test Stage (Validation & Testing) | Static analysis, deployment, integration, idempotency, and update testing.
Phase 4 — Validation & Completion (Production Readiness) | Code quality, functional validation, security validation, and stakeholder sign-off.
Current Key Roadblock
Dev — Observability (alerting) build is blocked: the Terraform service account lacks the required IAM roles (roles/monitoring.alertPolicyEditor, roles/monitoring.notificationChannelEditor) to create/manage alert policies. This also blocks Phase 3 Integration Testing's alert-policy verification step. Awaiting role grant.
Dev — What's Working / In Progress
• Instance provisioning validated for Standalone, HA, and DR topologies — all with PSC endpoints.
• Automated backups and scheduled snapshots validated.
• Code quality validation passed on the Valkey module.
• Self-service JSON-based consumer onboarding pattern in progress (create/delete via request file).
• Pending: connect to instance via a connection client to test reachability; IAM (client-auth) integration still pending.

## Dev
Terraform Module — Memorystore for Valkey ¦ Dev Environment Project Plan Goal: Build, test, validate and deliver a production-ready, self-service Terraform module that any consumer team can use to provision a fully-configured Valkey cache cluster on GCP
Status legend: | Completed | In Progress | Pending | Blocked | Not Started
PHASE | TASKS | SubComments | Start (date) | Finish (date) | Status | Owner | Key Contacts (Dependency)
PHASE 0 - REQUIREMENTS GATHERING - The objective of this project is to design, build, and deliver a standardized, production-ready Terraform module for deploying and managing Google Cloud Memorystore for Valkey instances. This module will enforce enterprise-grade standards across: Security, Availability, Networking, Observability, Cost governance | Consumer Inputs | Intake Form Variables UPDATE 7/28/2026: As per Siva's recommendation, ready the Terraform module for Valkey and publish it to the Terraform Registry, listing the variables that are actually required vs. defaulted. Module is ready — pending connect with Seyi to confirm the process to push modules to the registry. | 6/29/2026 |  | Pending | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Production Standards (Non-Negotiable) | Define and document: Security baseline, Availability SLAs, Observability requirements, Networking constraints (private access only) UPDATE 7/28/2026: TLS — certificate will be Google-managed CA per instance. IAM — manual process to pull groups into GCP and assign roles/memorystore.dbConnectionUser for client authentication (pending confirmation this is the correct role). Networking — PSC-based; we will be given the network host project and VPC name, and the module creates the PSC endpoint against the already-established connection policy. |  |  | Pending | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| GCP Access & Setup | Access to target GCP project (DATAHUB) API enablement validation Billing and quota verification RBAC role assignments requested for system accounts: AZ_PIM_GCP_Memstore_Admins_NPE (completed via AR3791958), AZ_PIM_GCP_Memstore_Admins_PROD (pending via AR3792429). | 6/30/2026 | 7/7/2026 | Completed | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase), Vicky Baldock for approvals
| Team Structure & Ownership | Teams involved (Cloud, Network, Security) Named contacts (owners) Roles and responsibilities UPDATE 7/28/2026: IMDG team owns the Terraform module. Siva will build a wrapper service on top of the module. Network team creates the connection policy and assists with subnet assignment in required regions. Security — manual process today (create groups, assign the dbConnectionUser role); automation is planned as a future enhancement. | 6/30/2026 |  | Pending | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Architecture & Design Review | Memorystore for Valkey architecture using Private Service Connect (PSC). Design review required for network topology, routing, PSC connectivity model, and subnet allocation strategy. | 6/29/2026 | 7/22/2026 | Completed | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| Terraform Platform Setup | Terraform state storage (GCS backend) Service accounts: Dev / QA / Prod environments IAM roles for Terraform execution GitHub repository access requested and completed through ARTASK113104926 and ARTASK113104893. Repos: AZ_GCP_CW_IT_MEMORYSTORE_VIEWER_NPE (AR3792491, completed), AZ_GCP_HUM_IT_MEMORYSTORE_VIEWER_NPE (AR3792463, completed), AZ_GCP_SS_IT_MEMORYSTORE_VIEWER_NPE (AR3792491, completed). | 6/30/2026 | 7/6/2026 | Completed | Satishkumar Sivakumar | Vicky Baldock for approvals
| Identity & Access | Google Groups mapping Workspace delegation AD / IAM group mappings for access control RBAC for AD group membership requested for: AZ_PIM_GCP_Memstore_Admins_NPE, PSC Deployer, Compute Network Viewer, DNS Resource Records Editor, Monitoring Admin, Tech Support Editor, Tech Support Viewer, Viewer. Google Group access completed: g_google_org_database_admins, g_google_org_viewers, G_GCP_SyncdUsers. | 6/30/2026 | 7/6/2026 | Completed | Satishkumar Sivakumar | Vicky Baldock for approvals
| Networking Design Considerations | PSC connectivity model Dedicated IP ranges/subnet planning Avoid IP range overlap Routing validation UPDATE 7/28/2026: Connection policies ready for NPE (Dev). Testing still pending — need code to reach and test the instance. | 7/7/2026 |  | Pending | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Pre-Production Checklist | Ensure: Networking readiness (VPC, subnets, firewall rules), no quota constraints, budget alerts configured, required APIs enabled UPDATE 7/28/2026: Networking readiness and Terraform instance setup access are ready; alert and notification policy setup still pending. |  |  | Pending | Satishkumar Sivakumar
PHASE 1 – Module Design (Architecture Phase) | Outputs & Integrations | Terraform outputs required: PSC endpoint / instance details Connection endpoints Notification channels: Email / PagerDuty UPDATE 7/28/2026: Outputs decided — instance details, connection details, PSC endpoints, and alert policy setup with the capability to notify app and platform teams. | 7/27/2026 |  | Pending | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Module Mapping | Info on root and sub-modules Identify reusable internal modules Standardize naming conventions Define input/output interfaces | 7/23/2026 |  | Pending | Satishkumar Sivakumar
| Dependency Planning | Establish execution order: Networking readiness Core instance deployment IAM bindings Observability setup | 8/1/2026 |  | Not Started
PHASE 2 – Code Build Stage (Implementation) | Input Variables | Finalize variables.tf (~40+ parameters) Include: descriptions, defaults where applicable, validation rules Core variable set validated through successful Dev deployments (Standalone / HA / DR); full parameter set with defaults and validation rules still being finalized ahead of registry publish. |  |  | In Progress | Satishkumar Sivakumar
| Core Resource Deployment | Memorystore Valkey instance creation configuration: memory sizing, replica configuration, and regional settings Successful in Dev: instance provisioning validated across Standalone, HA, and DR topologies, all with PSC endpoints. |  |  | Completed | Satishkumar Sivakumar
| Data Protection | Backup configuration and schedules, persistence setup Automated backups and scheduled snapshots validated in Dev. |  |  | Completed | Satishkumar Sivakumar
| Maintenance Configuration | Maintenance window definition and upgrade strategy |  |  | Not Started
| IAM Integration | Role bindings, service account permissions, group-based access Pending. Client-authentication IAM integration for instance connectivity not yet complete. |  |  | Pending | Satishkumar Sivakumar
| Production Guardrails | Deletion protection enabled, no public access, enforce private connectivity (PSC), secure defaults |  |  | Not Started
| Observability | Implement alerting policies: memory/CPU utilization thresholds, node health status, replication lag, connection spikes/errors. Integrations: Cloud Monitoring, notification channels Alert module in progress. ROADBLOCK: Terraform service account does not have the required IAM roles (roles/monitoring.alertPolicyEditor, roles/monitoring.notificationChannelEditor) to create/manage alert policies — awaiting role grant to proceed. |  |  | Blocked | Satishkumar Sivakumar
| Consumer Onboarding Pattern (Self-Service) | Self-service intake mechanism for consumer teams to request new instances or decommission existing ones. Building a JSON-based onboarding pattern: each consumer team drops a request JSON file (request_type: create/delete) into the onboarding-files folder. terraform apply merges global defaults, per-environment infra, and the request payload, and creates or deletes the instance accordingly on the next apply. |  |  | In Progress | Satishkumar Sivakumar
PHASE 3 – Code Test Stage (Validation & Testing) | Static Analysis | Terraform validation, linting checks |  |  | Not Started
| Deployment Testing | Deploy module in Dev environment, validate resource creation Module successfully deployed and instances created in Dev. |  |  | Completed | Satishkumar Sivakumar
| Integration Testing | Verify: instance provisioning, PSC connectivity, IAM roles applied correctly, alert policies created, backup schedules active Pending: connect to the instance via a connection client to validate reachability and test the instance. IAM role verification and alert-policy checks are blocked behind the Observability roadblock above. |  |  | Pending | Satishkumar Sivakumar
| Idempotency Testing | Run multiple terraform apply; ensure no unintended changes |  |  | Not Started
| Update Testing | Modify parameters; validate in-place updates with no destructive changes |  |  | Not Started
PHASE 4 – Validation & Completion (Production Readiness) | Code Quality | Zero validation errors, no hardcoded values, all variables documented, no secrets in code Code quality validation passed in the Valkey module. |  |  | Completed | Satishkumar Sivakumar
| Functional Validation | Instance creation successful; PSC endpoint auto-created and reachable from client network; alerts visible in Cloud Monitoring; test alerts trigger successfully; backups visible and restorable |  |  | Not Started
| Security Validation | No public endpoints, TLS enforced, IAM authentication configured, deletion protection enabled |  |  | Not Started
| Stakeholder Sign-Off | Required approvals: Cloud Team, Network Team, Security Team, IMDG Team |  |  | Not Started
Completion Criteria | All 4 phases are successfully delivered
All stakeholder sign-offs are obtained
Terraform module is production-ready and reusable
Consumer intake process is implemented
Module is handed over to Siva's Team
| Post-Deployment Success Criteria | Monitoring alerts functioning correctly No unexpected cost spikes Backups exist and are restorable Stable performance in production

## QA
Terraform Module — Memorystore for Valkey ¦ QA Environment Project Plan Goal: Build, test, validate and deliver a production-ready, self-service Terraform module that any consumer team can use to provision a fully-configured Valkey cache cluster on GCP
Status legend: | Completed | In Progress | Pending | Blocked | Not Started
PHASE | TASKS | SubComments | Start (date) | Finish (date) | Status | Owner | Key Contacts (Dependency)
PHASE 0 - REQUIREMENTS GATHERING - The objective of this project is to design, build, and deliver a standardized, production-ready Terraform module for deploying and managing Google Cloud Memorystore for Valkey instances. This module will enforce enterprise-grade standards across: Security, Availability, Networking, Observability, Cost governance | Consumer Inputs | Intake Form Variables |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Production Standards (Non-Negotiable) | Define and document: Security baseline, Availability SLAs, Observability requirements, Networking constraints (private access only) |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| GCP Access & Setup | Access to target GCP project (DATAHUB) API enablement validation Billing and quota verification |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase), Vicky Baldock for approvals
| Team Structure & Ownership | Teams involved (Cloud, Network, Security) Named contacts (owners) Roles and responsibilities |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Architecture & Design Review | Memorystore for Valkey architecture using Private Service Connect (PSC). Design review required for network topology, routing, PSC connectivity model, and subnet allocation strategy. |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| Terraform Platform Setup | Terraform state storage (GCS backend) Service accounts: Dev / QA / Prod environments IAM roles for Terraform execution |  |  | Not Started | Satishkumar Sivakumar | Vicky Baldock for approvals
| Identity & Access | Google Groups mapping Workspace delegation AD / IAM group mappings for access control |  |  | Not Started | Satishkumar Sivakumar | Vicky Baldock for approvals
| Networking Design Considerations | PSC connectivity model Dedicated IP ranges/subnet planning Avoid IP range overlap Routing validation |  |  | Not Started | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Pre-Production Checklist | Ensure: Networking readiness (VPC, subnets, firewall rules), no quota constraints, budget alerts configured, required APIs enabled |  |  | Not Started | Satishkumar Sivakumar
PHASE 1 – Module Design (Architecture Phase) | Outputs & Integrations | Terraform outputs required: PSC endpoint / instance details Connection endpoints Notification channels: Email / PagerDuty |  |  | Not Started | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Module Mapping | Info on root and sub-modules Identify reusable internal modules Standardize naming conventions Define input/output interfaces |  |  | Not Started | Satishkumar Sivakumar
| Dependency Planning | Establish execution order: Networking readiness Core instance deployment IAM bindings Observability setup |  |  | Not Started
PHASE 2 – Code Build Stage (Implementation) | Input Variables | Finalize variables.tf (~40+ parameters) Include: descriptions, defaults where applicable, validation rules |  |  | Not Started | Satishkumar Sivakumar
| Core Resource Deployment | Memorystore Valkey instance creation configuration: memory sizing, replica configuration, and regional settings |  |  | Not Started | Satishkumar Sivakumar
| Data Protection | Backup configuration and schedules, persistence setup |  |  | Not Started | Satishkumar Sivakumar
| Maintenance Configuration | Maintenance window definition and upgrade strategy |  |  | Not Started
| IAM Integration | Role bindings, service account permissions, group-based access |  |  | Not Started | Satishkumar Sivakumar
| Production Guardrails | Deletion protection enabled, no public access, enforce private connectivity (PSC), secure defaults |  |  | Not Started
| Observability | Implement alerting policies: memory/CPU utilization thresholds, node health status, replication lag, connection spikes/errors. Integrations: Cloud Monitoring, notification channels |  |  | Not Started | Satishkumar Sivakumar
| Consumer Onboarding Pattern (Self-Service) | Self-service intake mechanism for consumer teams to request new instances or decommission existing ones. |  |  | Not Started | Satishkumar Sivakumar
PHASE 3 – Code Test Stage (Validation & Testing) | Static Analysis | Terraform validation, linting checks |  |  | Not Started
| Deployment Testing | Deploy module in Dev environment, validate resource creation |  |  | Not Started | Satishkumar Sivakumar
| Integration Testing | Verify: instance provisioning, PSC connectivity, IAM roles applied correctly, alert policies created, backup schedules active |  |  | Not Started | Satishkumar Sivakumar
| Idempotency Testing | Run multiple terraform apply; ensure no unintended changes |  |  | Not Started
| Update Testing | Modify parameters; validate in-place updates with no destructive changes |  |  | Not Started
PHASE 4 – Validation & Completion (Production Readiness) | Code Quality | Zero validation errors, no hardcoded values, all variables documented, no secrets in code |  |  | Not Started | Satishkumar Sivakumar
| Functional Validation | Instance creation successful; PSC endpoint auto-created and reachable from client network; alerts visible in Cloud Monitoring; test alerts trigger successfully; backups visible and restorable |  |  | Not Started
| Security Validation | No public endpoints, TLS enforced, IAM authentication configured, deletion protection enabled |  |  | Not Started
| Stakeholder Sign-Off | Required approvals: Cloud Team, Network Team, Security Team, IMDG Team |  |  | Not Started
Completion Criteria | All 4 phases are successfully delivered
All stakeholder sign-offs are obtained
Terraform module is production-ready and reusable
Consumer intake process is implemented
Module is handed over to Siva's Team
| Post-Deployment Success Criteria | Monitoring alerts functioning correctly No unexpected cost spikes Backups exist and are restorable Stable performance in production

## UAT
Terraform Module — Memorystore for Valkey ¦ UAT Environment Project Plan Goal: Build, test, validate and deliver a production-ready, self-service Terraform module that any consumer team can use to provision a fully-configured Valkey cache cluster on GCP
Status legend: | Completed | In Progress | Pending | Blocked | Not Started
PHASE | TASKS | SubComments | Start (date) | Finish (date) | Status | Owner | Key Contacts (Dependency)
PHASE 0 - REQUIREMENTS GATHERING - The objective of this project is to design, build, and deliver a standardized, production-ready Terraform module for deploying and managing Google Cloud Memorystore for Valkey instances. This module will enforce enterprise-grade standards across: Security, Availability, Networking, Observability, Cost governance | Consumer Inputs | Intake Form Variables |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Production Standards (Non-Negotiable) | Define and document: Security baseline, Availability SLAs, Observability requirements, Networking constraints (private access only) |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| GCP Access & Setup | Access to target GCP project (DATAHUB) API enablement validation Billing and quota verification |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase), Vicky Baldock for approvals
| Team Structure & Ownership | Teams involved (Cloud, Network, Security) Named contacts (owners) Roles and responsibilities |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Architecture & Design Review | Memorystore for Valkey architecture using Private Service Connect (PSC). Design review required for network topology, routing, PSC connectivity model, and subnet allocation strategy. |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| Terraform Platform Setup | Terraform state storage (GCS backend) Service accounts: Dev / QA / Prod environments IAM roles for Terraform execution |  |  | Not Started | Satishkumar Sivakumar | Vicky Baldock for approvals
| Identity & Access | Google Groups mapping Workspace delegation AD / IAM group mappings for access control |  |  | Not Started | Satishkumar Sivakumar | Vicky Baldock for approvals
| Networking Design Considerations | PSC connectivity model Dedicated IP ranges/subnet planning Avoid IP range overlap Routing validation |  |  | Not Started | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Pre-Production Checklist | Ensure: Networking readiness (VPC, subnets, firewall rules), no quota constraints, budget alerts configured, required APIs enabled |  |  | Not Started | Satishkumar Sivakumar
PHASE 1 – Module Design (Architecture Phase) | Outputs & Integrations | Terraform outputs required: PSC endpoint / instance details Connection endpoints Notification channels: Email / PagerDuty |  |  | Not Started | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Module Mapping | Info on root and sub-modules Identify reusable internal modules Standardize naming conventions Define input/output interfaces |  |  | Not Started | Satishkumar Sivakumar
| Dependency Planning | Establish execution order: Networking readiness Core instance deployment IAM bindings Observability setup |  |  | Not Started
PHASE 2 – Code Build Stage (Implementation) | Input Variables | Finalize variables.tf (~40+ parameters) Include: descriptions, defaults where applicable, validation rules |  |  | Not Started | Satishkumar Sivakumar
| Core Resource Deployment | Memorystore Valkey instance creation configuration: memory sizing, replica configuration, and regional settings |  |  | Not Started | Satishkumar Sivakumar
| Data Protection | Backup configuration and schedules, persistence setup |  |  | Not Started | Satishkumar Sivakumar
| Maintenance Configuration | Maintenance window definition and upgrade strategy |  |  | Not Started
| IAM Integration | Role bindings, service account permissions, group-based access |  |  | Not Started | Satishkumar Sivakumar
| Production Guardrails | Deletion protection enabled, no public access, enforce private connectivity (PSC), secure defaults |  |  | Not Started
| Observability | Implement alerting policies: memory/CPU utilization thresholds, node health status, replication lag, connection spikes/errors. Integrations: Cloud Monitoring, notification channels |  |  | Not Started | Satishkumar Sivakumar
| Consumer Onboarding Pattern (Self-Service) | Self-service intake mechanism for consumer teams to request new instances or decommission existing ones. |  |  | Not Started | Satishkumar Sivakumar
PHASE 3 – Code Test Stage (Validation & Testing) | Static Analysis | Terraform validation, linting checks |  |  | Not Started
| Deployment Testing | Deploy module in Dev environment, validate resource creation |  |  | Not Started | Satishkumar Sivakumar
| Integration Testing | Verify: instance provisioning, PSC connectivity, IAM roles applied correctly, alert policies created, backup schedules active |  |  | Not Started | Satishkumar Sivakumar
| Idempotency Testing | Run multiple terraform apply; ensure no unintended changes |  |  | Not Started
| Update Testing | Modify parameters; validate in-place updates with no destructive changes |  |  | Not Started
PHASE 4 – Validation & Completion (Production Readiness) | Code Quality | Zero validation errors, no hardcoded values, all variables documented, no secrets in code |  |  | Not Started | Satishkumar Sivakumar
| Functional Validation | Instance creation successful; PSC endpoint auto-created and reachable from client network; alerts visible in Cloud Monitoring; test alerts trigger successfully; backups visible and restorable |  |  | Not Started
| Security Validation | No public endpoints, TLS enforced, IAM authentication configured, deletion protection enabled |  |  | Not Started
| Stakeholder Sign-Off | Required approvals: Cloud Team, Network Team, Security Team, IMDG Team |  |  | Not Started
Completion Criteria | All 4 phases are successfully delivered
All stakeholder sign-offs are obtained
Terraform module is production-ready and reusable
Consumer intake process is implemented
Module is handed over to Siva's Team
| Post-Deployment Success Criteria | Monitoring alerts functioning correctly No unexpected cost spikes Backups exist and are restorable Stable performance in production

## Prod
Terraform Module — Memorystore for Valkey ¦ Prod Environment Project Plan Goal: Build, test, validate and deliver a production-ready, self-service Terraform module that any consumer team can use to provision a fully-configured Valkey cache cluster on GCP
Status legend: | Completed | In Progress | Pending | Blocked | Not Started
PHASE | TASKS | SubComments | Start (date) | Finish (date) | Status | Owner | Key Contacts (Dependency)
PHASE 0 - REQUIREMENTS GATHERING - The objective of this project is to design, build, and deliver a standardized, production-ready Terraform module for deploying and managing Google Cloud Memorystore for Valkey instances. This module will enforce enterprise-grade standards across: Security, Availability, Networking, Observability, Cost governance | Consumer Inputs | Intake Form Variables |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Production Standards (Non-Negotiable) | Define and document: Security baseline, Availability SLAs, Observability requirements, Networking constraints (private access only) |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| GCP Access & Setup | Access to target GCP project (DATAHUB) API enablement validation Billing and quota verification |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase), Vicky Baldock for approvals
| Team Structure & Ownership | Teams involved (Cloud, Network, Security) Named contacts (owners) Roles and responsibilities |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong, Seyi Babaniji (guided discovery phase)
| Architecture & Design Review | Memorystore for Valkey architecture using Private Service Connect (PSC). Design review required for network topology, routing, PSC connectivity model, and subnet allocation strategy. |  |  | Not Started | Satishkumar Sivakumar | Siva Rajadurai, William Duong
| Terraform Platform Setup | Terraform state storage (GCS backend) Service accounts: Dev / QA / Prod environments IAM roles for Terraform execution |  |  | Not Started | Satishkumar Sivakumar | Vicky Baldock for approvals
| Identity & Access | Google Groups mapping Workspace delegation AD / IAM group mappings for access control |  |  | Not Started | Satishkumar Sivakumar | Vicky Baldock for approvals
| Networking Design Considerations | PSC connectivity model Dedicated IP ranges/subnet planning Avoid IP range overlap Routing validation |  |  | Not Started | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Pre-Production Checklist | Ensure: Networking readiness (VPC, subnets, firewall rules), no quota constraints, budget alerts configured, required APIs enabled |  |  | Not Started | Satishkumar Sivakumar
PHASE 1 – Module Design (Architecture Phase) | Outputs & Integrations | Terraform outputs required: PSC endpoint / instance details Connection endpoints Notification channels: Email / PagerDuty |  |  | Not Started | Satishkumar Sivakumar | Connect with Siva Rajadurai, William Duong after completing first draft of Valkey module
| Module Mapping | Info on root and sub-modules Identify reusable internal modules Standardize naming conventions Define input/output interfaces |  |  | Not Started | Satishkumar Sivakumar
| Dependency Planning | Establish execution order: Networking readiness Core instance deployment IAM bindings Observability setup |  |  | Not Started
PHASE 2 – Code Build Stage (Implementation) | Input Variables | Finalize variables.tf (~40+ parameters) Include: descriptions, defaults where applicable, validation rules |  |  | Not Started | Satishkumar Sivakumar
| Core Resource Deployment | Memorystore Valkey instance creation configuration: memory sizing, replica configuration, and regional settings |  |  | Not Started | Satishkumar Sivakumar
| Data Protection | Backup configuration and schedules, persistence setup |  |  | Not Started | Satishkumar Sivakumar
| Maintenance Configuration | Maintenance window definition and upgrade strategy |  |  | Not Started
| IAM Integration | Role bindings, service account permissions, group-based access |  |  | Not Started | Satishkumar Sivakumar
| Production Guardrails | Deletion protection enabled, no public access, enforce private connectivity (PSC), secure defaults |  |  | Not Started
| Observability | Implement alerting policies: memory/CPU utilization thresholds, node health status, replication lag, connection spikes/errors. Integrations: Cloud Monitoring, notification channels |  |  | Not Started | Satishkumar Sivakumar
| Consumer Onboarding Pattern (Self-Service) | Self-service intake mechanism for consumer teams to request new instances or decommission existing ones. |  |  | Not Started | Satishkumar Sivakumar
PHASE 3 – Code Test Stage (Validation & Testing) | Static Analysis | Terraform validation, linting checks |  |  | Not Started
| Deployment Testing | Deploy module in Dev environment, validate resource creation |  |  | Not Started | Satishkumar Sivakumar
| Integration Testing | Verify: instance provisioning, PSC connectivity, IAM roles applied correctly, alert policies created, backup schedules active |  |  | Not Started | Satishkumar Sivakumar
| Idempotency Testing | Run multiple terraform apply; ensure no unintended changes |  |  | Not Started
| Update Testing | Modify parameters; validate in-place updates with no destructive changes |  |  | Not Started
PHASE 4 – Validation & Completion (Production Readiness) | Code Quality | Zero validation errors, no hardcoded values, all variables documented, no secrets in code |  |  | Not Started | Satishkumar Sivakumar
| Functional Validation | Instance creation successful; PSC endpoint auto-created and reachable from client network; alerts visible in Cloud Monitoring; test alerts trigger successfully; backups visible and restorable |  |  | Not Started
| Security Validation | No public endpoints, TLS enforced, IAM authentication configured, deletion protection enabled |  |  | Not Started
| Stakeholder Sign-Off | Required approvals: Cloud Team, Network Team, Security Team, IMDG Team |  |  | Not Started
Completion Criteria | All 4 phases are successfully delivered
All stakeholder sign-offs are obtained
Terraform module is production-ready and reusable
Consumer intake process is implemented
Module is handed over to Siva's Team
| Post-Deployment Success Criteria | Monitoring alerts functioning correctly No unexpected cost spikes Backups exist and are restorable Stable performance in production